## overview
Task | Priority | Type | Estimate (Worst Case) | Phase
main menu:
background image | high | art | 8 | 4
opening story cutscene:
change wording to reflect a theme of learning | high | dialog/art | 3 | 4
pre-crash fixes:
clearer delivery zone/trigger zone for journal miniquest | low | bug | 1 | 4
clearer trigger zone for box raising/lowering miniquest | low | bug | 1 | 4
fix dialog of stowaway if you find the pizza first | low | dialog | 0.5 | 4
conversation w/ Navigator (maybe tweak to make less overtly anti-religion, perhaps focus on learning?) | low | dialog | 0.5 | 5
star map doesn't appear! (saw this after full fix) | high | bug | 2 | 2
crash cutscene:
art (8 frames) | high | art | 24 | 4
narrator dialog: "Jerrod was about to meet the real main character of this story...me." | high | dialog | 4 | 4
post-crash fixes:
city art | high | art | 2 | 4
add a few extra levels/tweak difficulty | high | level design | 8 | 1
add creeping veins | high | art | 16 | 4
change around dialog so that it's less "in the middle" of the platforming. | high | level design | 3 | 1
boss battle art:
platform attacks | high | art | 16 | 4
growing attack | high | art/code | 6 | 4
"pressure" kill wall | high | art | 4 | 4
outer veins | high | art | 4 | 4
eye pupils | high | art/code | 8 | 4
fixes/lingering design problems:
resetting boxes that fall out of bounds | high | bug | 2 | 2
throwing guide disappeared | low | bug | 2 | 5
crouch w/ carry animation busted | high | bug | 3 | 2
scrap doesn't always collect like it should | high | bug | 6 | 2
124

## gannt
Week | week 1 | [5 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 5 | [6 empty] | week 6 | [6 empty] | week 7 | [6 empty] | week 8 | [6 empty] | week 9 |  |  |  |  | alpha
Day | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S | Su | M | T | W | TH | F | S
Date | time axis 2021-02-09 to 2021-04-03
Hours Available | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 0 | 3 | 3 | 3 | 3 | 3 | 8
Phases | 2021-02-09: import boss art
1 - design tasks | 2021-02-11: design tasks
2 - high priortiy bugs | 2021-02-13: high priority bugs
3 - testing pass | 2021-02-19: testing
4 - dialog & art related tasks | 2021-02-20: dialog & art related tasks
5 - low priority bugs | 2021-03-21: low priority bugs
6 - testing & polish | 2021-03-23: testing/polish
7 - release testing | 2021-04-02: final playtest

## design tasks
Task | Priority | Type | Estimate (Worst Case)
add a few extra levels/tweak difficulty | high | level design | 8
change around dialog so that it's less "in the middle" of the platforming. | high | level design | 3

## bugs
Task | Priority | Type | Estimate (Worst Case)
star map doesn't appear! (saw this after full fix) | high | bug | 2
resetting boxes that fall out of bounds | high | bug | 2
crouch w/ carry animation busted | high | bug | 3
scrap doesn't always collect like it should | high | bug | 6
clearer delivery zone/trigger zone for journal miniquest | low | bug | 1
clearer trigger zone for box raising/lowering miniquest | low | bug | 1
throwing guide disappeared | low | bug | 2

## art tasks
Task | Priority | Type | Estimate (Worst Case)
main menu background image | high | art | 8
opening cutscene: change wording to reflect a theme of learning | high | dialog/art | 3
crash cutscene art (8 frames) | high | art | 24
city art | high | art | 2
post crash: add creeping veins | high | art | 16
platform attacks | high | art | 16
growing attack | high | art/code | 6
"pressure" kill wall | high | art | 4
outer veins | high | art | 4
eye pupils | high | art/code | 8
91

## dialog tasks
Task | Priority | Type | Estimate (Worst Case)
fix dialog of stowaway if you find the pizza first | low | dialog | 0.5
conversation w/ Navigator (maybe tweak to make less overtly anti-religion, perhaps focus on learning?) | low | dialog | 0.5
crash cutscene narrator dialog: "Jerrod was about to meet the real main character of this story...me." | high | dialog | 4